## ACTIVITYLOG
ID | timestamp | activity | type | Follow up | STATUS | REFERENCE ID | ETA
1 | 2026-07-27 08:00 | first day. receiving laptop, appliances and tools | LOG |  | LOG
2 | 2026-07-27 13:00 | Exploring documentation, EasyPlant and TJJV Sharepoints | LOG |  | LOG
3 | 2026-07-28 13:00 | Weekly CSU meeting with Thierry. Open points for INST: -Vendor certificates for calibration against DS -> assign someone from Inst team - moisture analyzers only one is purchased, to be moved around the FLNG until Offshore - functional test plan for SIF (Fabio to prepare document section against FSA3 and IEC requirements) - FMR for temporary OWS already issued -> follow up receiving status - update LOTO pins for isolation on PDPs and Control Cabinets -> Syukri - agreed for INST isolation register with common Excel file - define personnel that will act as isolation authority in INST TEAM | LOG |  | LOG
4 | 2026-07-29 13:00 | Kickoff meeting with Thierry and Syukri on INST manpower, resources and plans Topics discussed as below: 1. Orga / bar charts - Orga chart to be prepared based on Annex A4 - Instrum & Ctrl annex A 4 bar chart shall be adjusted if necessary based on the Orga - Target mid August 2026 2. Procedures TJS -> Vysus FSA3 - Loop test procedure -> By 31st of July - Functional test proc -> By Mid of August 2026 – SIF procedure to be attached to the functional test proc as annex - SHI functional test procedure to be recovered from SHI 3. CSU tools & COM spares purchasing / Tempo HVAC - CSU tools -> Clarifications to be completed by 31st of July - COM spares are to be ordered to cover until RFSU - FMR for spare parts to be issued by end of 2026 - FMR_CSU & FMR_CSUSP from Coral South to be used as reference - Unpriced POs can be used to find the construction spares 4. VMRs for Instrum vendors - Emerson VMR was issued (field + ICSS) -> Follow up reviews to be initiated - VMR for Siemens for the PLCs (trouble shooting & network issues) -> To be proposed - Other VMRs -> Only for purely instrumentation systems (packages will be arranged by process/utility teams) - Alarm rationalization TBD with Guillaume -> End of August 5. EP and ITRs B loading - EP all digital -> Only ITR B digital, but attachement via filling clecks. PLs are digital also if photos can be added or sent to the PL Coordinator. PL validation by PL coordinator 6. LOTO, BPO, TPC, trainings & LR - LOTO -> to prepare the LOTO register for instrum panels/PDB + assign dedicated personnel - Trainings -> Ensure with Orga to define the roles AA, IA, PR, PA, etc …., L2b, IECEx (define Ex002/Ex004) for Ex 001 price will be requested to SHI - On boarding slides/training -> To be prepared for the team - No requirement for SIF testing competence - BPO & TPC -> Structure the process -> Orga to be adjusted - LR witnessing approach -> Notification of start of Subsystem (24 hrs in advance) 7. CCMS & LL analysis and additional CS issues not covered - To be check the accesses. Tables to be review along with project progress 8. Loop folder preparation & EP data base review (including change on AFDS) - Hard copies loop folders / Use auto tool or not / collect/compile documentation / Cross check EP population at the same time 9. ITR A for verif of calib certs vs data sheets PT & TT - Collection of vendor calibration certs -> Assign 1 resource to check cert vs DS 10. Schedule review - CRDs follow latest JV assumptions - KPIs provide estimated ITR B workfront in time - L1 Schedule with SHI dates provides summary overview | LOG | update the folder links and share across leads | LOG
5 | 2026-07-29 15:50 | Update folder links from item 4 | TASK | Fabio | ASSIGNED | 4 | 2026-08-20
6 | 2026-07-29 16:00 | Temporary HVAC installation details. mainly for ELE team for now | LOG |  | LOG
7 | 2026-07-30 08:00 | Complete UIR and LAB Addressable database for EasyPlant | LOG |  | LOG
8 | 2026-07-30 13:00 | Complete TIR Addressable database for EasyPlant | LOG |  | LOG
9 | 2026-07-30 15:00 | Share interactive room layout of the FLNG to be add to the welcome package for new teams members - note: drawings to be updated | LOG |  | LOG
10 | 2026-07-30 16:00 | Give Yernar to find new drawings and update item ID 9 - Shiproom layout | TASK | Yernar |  | 9 | 2026-08-29
11 | 2026-07-31 08:00 | Complete BITR-I10 database for Hull to be sent to Completion team
12 | 2026-07-31 15:00 | sent email to Completion team NEW B-ITR-I10 ADDRESSABLE FIRE & GAS LOOP TEST to add, and 33 to be removed This is the recap quantities for ADDRESSABLE LOOPS - B-ITR-I10: LQ-HULL 2076 TOPSIDE 256 TO BE REMOVED 33 Source: C:\Users\fmatricard\Documents\CoralNorth\BITR-studies
13 | 2026-07-31 16:00 | Discussed with Guillame missing documentation for Addressable detailed diagrams for Hull/LQ sent email to SHI (taekyung.ok@samsung.com) for clarification - SHI Autronica addressable wiring --- Hi TK, Please could you tell us where to find the detail wiring of the Addressable detectors connected to Autronica system. I found something strange in the Wiring Diagram for Instrumentation in Hull – LQ 4424LQDIEH50120, if possible please explain us how it is wired or tell us if there is other documents to refer. | LOG | wait for 12 August and follow up |  |  | 2026-08-28
14 | 2026-08-03 08:38 | Task assignment for item 3 - follow up for MAV servers for DeltaV upgrade in Korea Emerson ETA 17/18 August | TASK | Syukri |  | 3
15 | 2026-08-03 10:00 | Safety Training - room 3 | LOG |  | LOG
16 | 2026-08-03 13:00 | FSA3 requirements and IEC for SIF testing - preparations for Functional test procedure | LOG |  | LOG
17 | 2026-08-03 15:00 | find clause and details in IEC 61511 rev 2016 for SIF testing | LOG |  | LOG
18 | 2026-08-04 08:38
19 | 2026-08-04 10:00
20 | 2026-08-04 13:00
21 | 2026-08-04 15:00
22 | 2026-07-28 08:00 | Complete PIR Addressable database for EasyPlant | LOG |  | LOG
23 | 2026-07-29 08:00 | Complete SIR Addressable database for EasyPlant | LOG |  | LOG
24 | 2026-08-03 09:00 | Items to remember for CSU, sent to Thierry - N2 purge on Diesel GTG lines as permissive for GTG start suring BOR - to be fixed | TODO | send details to Thierry Guillaume |  |  | 2026-08-28
25 | 2026-08-03 09:38 | Items to review from CSU as process issues: - fresh water generators RUPTURE DISKS - WHRU sequence with GTG startup - FW and CW MOV valves fault/moving during startup sequence | TODO | send details to Thierry Guillaume
26 | 2026-08-03 11:30 | Assign ROSA to study and collect relevant architecture and details for PLC network | TASK | Rosa
27 | 2026-08-03 12:02 | Follow up Autronica HULL/LQ reply from SHI | TASK | fabio | ASSIGNED | 13 | 2026-08-12

## dropdowns
TYPE | STATUS
LOG | PENDING
TODO | ASSIGNED
TASK | ONGOING
COMPLETED
LOG